## Summary
Date | 2014-11-11
Test Release Version | 1.3.2T
Test Document Version | 1.0.0
Tested By | -
-
-
-
Approved By | -
Signed By | -
Document Tracability Matrix
SRS
CR

## Tests
# | Component | Referning Document | CRN / FRN | State of Enviroment | Test Limitations | Test Case | Description | Expected Outcome | Test Result | Severity | Tested By | Comments | Action
1 | Setup Wizard |  |  | New Seebo Bootup | Must not click Next after the Thank you page. | Setup Wizard Forward Flow | Click on Next / Agree on each page | Clicking on Next/Agree should take to the next page. Forward Flow: Welcome, Do you agree?, Tune Live TV, Connect Wifi, Thank You. | PASS |  | TD
2 | Setup Wizard |  |  | New Seebo Bootup |  | Setup Wizard Backward Flow | Click on Back | Clicking on Back should take to the previous page upto the “Do you agree?” Page . See above for Page flow | PASS |  | TD
3 | Setup Wizard |  |  | New Seebo Bootup |  | Disagree TOC | Click “Disagree” on the Do you agree? Page | Should take you to the “No” page. Text should be wrapped properly within text area. No spelling typo. New international phone number (+61 3 8368 6800) should be available. | PASS |  | TD
4 | Setup Wizard |  |  | New Seebo Bootup, DVBT connected to Anteanna |  | Tune Live TV | Default region must be “auto-tune-Australia” | When user gets the region list “auto-tune-Australia” would be the default region to select. | PASS |  | TD | We tested for au_Melbourne.
5 | Setup Wizard |  |  | New Seebo Bootup, DVBT connected to Anteanna |  | Tune Live TV | Select “auto-tune-Australia” and Tune | Message : Lost Connection to VDR followed by approximately 12 mins of tuning. After tuning is done PVR DB should be automatically reset and Connection to VDR should be Established. | PASS |  | TD | We tested for au_Melbourne and took around 3-4 mins.
6 | Setup Wizard |  |  | New Seebo Bootup, DVBT connected to Anteanna |  | Tune Live TV | Select “auto-tune-Australia” and Tune | User Dialouge TEXT should be aligned with Region ( “auto-tune-Australia”) drop down text menu box. The text “Now tuning... should appear with approximately a 10px space gap between the progress bar. Those texts are aligned (left) with the selection group box. | PASS |  | TD
7 | Setup Wizard |  |  | Seebo in proximity of Wifi. RJ45 unpluged (Wire Internet – For testing in Australia) |  | Connect Wifi | Connect to a known Wifi | Must pick and display the all available network connections. Should successfully Connect to Wifi. | PASS |  | TD
8 | Setup Wizard |  |  |  |  | Try to connect to any available network connection(s) | Properly handled "Incorrect Password error" which appeared before, for all types of errors. Now it comes for real input (password) errors. For network connection errors we now display the correct error for 8 seconds. | Should connect without issues. Should get appropriate error message. Message should display 8 secs. | UNTESTED
9 | Setup Wizard |  |  |  |  | Connect Wifi | When you click “Next” PVR DB should reset. |  | PASS |  | TD
10 | Setup Wizard |  |  |  |  | Wifi display text | Should not contain '-' sign | No '-' was available in the Wifi word. | PASS |  | TD
11 | Setup Wizard |  |  |  |  | Settings-> Networks | No “Back” button | There should not be any “Back” button and back functionality must be handle by back button in the remote/keyboard | PASS |  | TD
12 | Setup Wizard |  |  |  |  | Settings-> System info | No “Back” button | There should not be any “Back” button and back functionality must be handle by back button in the remote/keyboard | PASS |  | TD
13 | Setup Wizard |  |  |  |  | Settings-> System info | No XBMC word available | Replaced the “Seebo's modified XBMC” by Seebo <latest version number> Ex: Seebo 1.3.5 | PASS |  | TD
14 | Setup Wizard |  |  |  |  | Settings-> Networks-> T&C/Privacy | New international support number should be updated | New international phone number (+61 3 8368 6800) should be available. | PASS |  | TD
15 | Setup Wizard |  |  |  |  | Settings-> Appearance-> Skin-> Skin | Seebo logo should appear |  | PASS |  | TD
16 | Setup Wizard |  |  | Seebo booted for the second time |  |  |  | Setup Wizard should not run | PASS |  | TD
17 | Global Menu List |  |  |  |  | Select any global menu option | Should display the correct menu option name on top. | Example: Click OnDemand: Global Menu List should be on top and OnDemand should be highlighted and focused. | PASS |  | TD
18 | Settings |  |  |  |  | Select Settings from Menu |  | Pictures and Profiles should be removed | PASS |  | TD
19 | Settings |  |  |  |  | Select Each Sub Setting |  | All instances of xbmc should be replaced with Seebo | PASS |  | TD
20 | Settings |  |  |  |  | Reset PVR DB | Settings-> LiveTV-> General-> Reset the PVR Database | PVR Database should be reset | PASS |  | TD
21 | Settings |  |  |  |  | Reset EPG DB | Settings-> Live TV-> EPG-> Reset the EPG Database | EPG Database should be reset | PASS |  | TD
22 | Settings |  |  |  |  | Check Zoom level | Settings-> Appearance-> Skin | Zoom should be at -2% | PASS |  | TD
23 | Settings | [5 empty] | Settings-> Network-> Tune Live TV-> Select auto-tune-Australia and Tune | Messge : Lost Connection to VDR followed by approximately 12 mins of tuning. After tuning is done PVR DB should be reset and Connection to VDR should be Established
24 | Settings |  |  |  |  | Settings->Network-> Connections | Fixed the layout issues | No text overlapping. Correct data should be available under relevant column. | PASS |  | TD
25 | Settings |  |  |  |  | Settings->Network-> Connections | Try to connect to any available network connection(s) | Properly handled "Incorrect Password error" which appeared before, for all types of errors. Now it comes for real input (password) errors. For network connection errors we now display the correct error for 8 seconds. | UNTESTED |  | TD
26 | Settings |  |  |  |  | Settings->Network-> Connections | Input an incorrect password to a WiFi connection click Done | "Incorrect Password - Input error" error message is displayed | UNTESTED |  | TD
27 | Settings |  |  |  |  | Settings->Network-> Connections | Does not input any password and click Done. | "Enter a Valid Password - Input Error" message is displayed | UNTESTED
28 | Settings |  |  |  |  | Settings->Network-> Connections | If the connection is broken or any other issues | "Did not receive a reply. Possible causes include: the reply timeout expired or the network connection was broken." | UNTESTED
29 | Settings |  |  | Seebo booted for the second time |  | Settings->Network-> Connections |  | Wifi Connection should be auto established | PASS |  | TD
30 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Placement of “Help” |  | “Help” should be placed in between “Settings” and “OnDemand” | PASS |  | TD
31 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” |  | Two buttons should appear at the top. Buttons are, “How To” and “Support” A Label "Notice Board" and a text box containing past update information is displayed. Only if we have long text, it should scroll | PASS |  | TD
32 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” | Behaviour of "How to" button | - On seletion => "How To" button should highlighted as in the theme - On Left => No Action - On Right => Selection move to right highlighting "Support" button - On Up => No Action - On Down => No Action - On Back => Main Menu should appear - On Menu => No Action - On Click => Load "How To" WIndow |  |  | TD | After select Help, cant go back to Main Menu by click “up”. (can be done by click BACK). Need to implement that to uniformalise with other sections (LiveTV, OnDemand, etc.) (FIXED in 1.3.5RC2)
33 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” | Behaviour of "Support" button | - On seletion => "Support" button should highlighted as in the theme - On Left => Selection move to left highlighting "How To" button - On Right => No Action "Support" button - On Up => No Action - On Down => No Action - On Back => Main Menu should appear - On Menu => No Action - On Click => Load "Support" WIndow | PASS |  | TD
34 | Help | SeeboHelpRA.pdf(v1.3.5) |  | If any videos is playing in the background and user is navigating |  | Main Menu → “Help” | Behaviour of background visualization | Background video play should continue | PASS |  | TD | But it stops when select How To, do we expect that ?
35 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → back button clicked |  | Main Menu should appear with "Help" is selected | PASS |  | TD
36 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → How To | Layout of the "How To" window | Layout should be same as in the page 3, SeeboHelpRA.pdf | PASS |  | TD
37 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → How To | Behaviour of "How To" navigation panel | ■11 Items should be listed as explained in the page3, SeeboHelpRA.pdf ■Each Button - On Left => No Action - On Right => No Action - On Up => Selection move the above itme in the list - On Down => Selection move tothe below item in the list ☼ On Up of top most item will move the selection to bottom most item ☼ On Down of bottom most item will move the selection to top most item ■ Button Texts are longer then button width, will slide inside the button when the button is selected | PASS |  |  | We got only 9 videos from Pat. Still we didnt get the rest two videos. | New videos sent on 26/02/2015.
38 | Help | SeeboHelpRA.pdf(v1.3.5) |  | No Help Videos are playing |  | Main Menu → “Help” → How To → Click on Navigation panel video item | Behaviour of video play | corresponding video should start to play | PASS |  | TD
39 | Help | SeeboHelpRA.pdf(v1.3.5) |  | While some other help video is playing |  | Main Menu → “Help” → How To → Click on Navigation panel video item | Behaviour of video play | Current playing video should stop playing and Correspoinding video for selection, should start playing | PASS |  | TD
40 | Help | SeeboHelpRA.pdf(v1.3.5) |  | No Help Videos are playing |  | Main Menu → “Help” → How To → back button click | Leaving "How To" window | Help window should appear. | PASS |  | TD
41 | Help | SeeboHelpRA.pdf(v1.3.5) |  | While some other help video is playing |  | Main Menu → “Help” → How To → Click on navigatoin panel video item → back button click | Leaving "How To" window | ■Help window should appear. ■The video which was playing should stop | PASS |  | TD
42 | Help | SeeboHelpRA.pdf(v1.3.5) |  | On Demand video is playing in the background and user is navigating |  | Main Menu → “Help” → How To | Behaviour of background visualizationi | Background video play should stop | PASS |  | TD
43 | Help | SeeboHelpRA.pdf(v1.3.5) |  | Live TV video is playing in the background and user is navigating |  | Main Menu → “Help” → How To | Behaviour of background visualizationi | Background video play should stop | PASS |  | TD
44 | Help | SeeboHelpRA.pdf(v1.3.5) |  | Music is playing in the visualization is in the background and user is navigating |  | Main Menu → “Help” → How To | Behaviour of background visualizationi | Background visualizaton should stop | PASS |  | TD
45 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” →Support | Layout of the "Suport" window | Layout should be same as in the page 4, SeeboHelpRA.pdf | PASS |  | TD
46 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → Support | Behaviour of "Support" navigation panel | ■3 Items should be listed as explained in the page4, SeeboHelpRA.pdf ■Each Button - On Left => No Action - On Right => No Action - On Up => Selection move the above itme in the list - On Down => Selection move tothe below item in the list Information should be correct and up-to-date.
47 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → Suport → Click on Contact | Layout of contact | Layout should be same as in the page 4, SeeboHelpRA.pdf | PASS |  | TD
48 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → Support → Click on Contact | Layout of Warranty | Layout should be same as in the page 5, SeeboHelpRA.pdf Since this is long text, it should scroll | PASS |  | TD
49 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → Support → Click on Contact | Layout T&C's | Layout should be same as in the page 6, SeeboHelpRA.pdf Since this is long text, it should scroll | PASS |  | TD
50 | Help | SeeboHelpRA.pdf(v1.3.5) |  |  |  | Main Menu → “Help” → Suport → Click on navigatoin panel item → back button clicked | leaving "Support" Menu | Help window should appear. | PASS |  | TD
51 | Music |  |  |  |  | Music-> Play a Radio Channel |  | TuneIn Radio, VEVO, TripleRRR & Radio Tunes should be there | PASS |  | TD | Some sections of Tueln Radio requires an account.
52 | Music |  |  |  |  | Back button will carry the user to the home menu. Removed the old functionality and moved those to context menu options in Music. | Check this option: Add source in the context menu on Music |  | PASS |  | TD
53 | On Demand |  |  | New Seebo Bootup |  | Select On Demand |  | 1Channel ABC iVIEW AFL Video Best Of YouTube Betty's Kitchen Daily Motion CBS News Food Network GoPro REDBULL SeeDocs Sports Illustrated Ted Talks TMZ Victoria's Secret World News Live WWE Online YouTube VEVO TV4ME | PASS |  | TD | Refer: SM-1.3.4.23_02_2015.xls Updated, Foodnetwork, Sports Illustrated, Ted Talks, World New Live, YouTube, SeeDocs Did not upgrade 1Channel and TV4ME (even though they have release new versions) | Old content of TVM4ME doesnt work (but this is a known problem)
54 | OnDemand |  |  |  |  | Install GetMore addons |  | Install addons from GetMore without errors. Common addons are (1Channels, Navi-X, TV4ME, MashUp, Icefilms) | PASS |  | TD | The “wokr-around” for dependencies issue is only temporaliry. Need to imgrate OE5's Python lib
55 | On Demand |  |  | YouTube |  | OnDemand->YouTube->Search | No old cache search phrases. | End-use must get cache free search option | PASS |  | TD
56 | On Demand |  |  | Playing the video with YouTube. Functional Internet Connection |  | All YouTube videos must play irrespective of the region | Seebo Australia sometimes has DNS problems, hence may fail to play video. But this fails the condition of functional Internet. Symptom: “Error 110: failed to open url” message appears. A quick workaround (only when this problem occurs is to use Google DNS: Settings->Networks->Connections-><Select the Internet IP>-> Edit-> DNS-> <Change to 8.8.8.8> -> Save | Make sure the YouTube videos are playing in Australia | PASS |  | TD | Check the same in AUS.
57 | On Demand |  |  | Playing 3rd party channels via youtube player. Functional Internet Connection |  | All YouTube videos must play irrespective of the region and without any errors |  | Make sure the all 3rd party videos playing through YouTube player. | PASS |  | TD | None of the videos are playing in VEVO in SL. TV4ME: Some of them are playing. 1Channel: Most of them are playing
58 | On Demand |  |  | Playing the video with VEVO. Functional Internet Connection |  | Both VEVO and VEVO videos play via YouTube must must play irrespective of the region |  | Make sure the VEVO and videos playing via YouTube are playing in Australia | PASS |  | TD | Most of the VEVO videos can play via YouTube channel
59 | On Demand |  |  | New Seebo Bootup | Addons are not in our control | Play On Demand Content |  | No Errors | PASS |  | TD | Only check Navi-X
60 | On Demand |  |  | New Seebo Bootup |  | Play Content from SeeDocs |  | No Errors | PASS |  | TD
61 | On Demand |  |  | New Seebo Bootup |  | On Demand-> Get More |  | Most Icons should be visible (no delays) | PASS |  | TD
62 | On Demand |  |  |  |  | Back button will carry the user to the home menu. Removed the old functionality and moved those to context menu options in OnDemand. | Check these options: Files, Playlists in the context menu on OnDemand. |  | PASS |  | TD
63 | Live TV |  |  | Live TV already Tuned |  | Live TV-> Browse Channels | These LiveTV channel should be available by default | Current available IPTV channels, RT Gotica TV HSN TV TLC USTwit Rocks&Co (To be removed) Newly added IPTV Channels, QVC Extra Pac 12 The Pentagon VTV Aljazeera (Live) USA Basketball Outdoor Channel | PASS |  | TD | But we didnt get any confirmation on these two IPTV channels from AUS. USA Basketball Outdoor Channel Rock&Co: Since 1.3.5 is not officially released, we didnt remove this from m3u file in FTP server. But we tested in locally after removing this. We will be sending the updated (for 1.3.5) playlist.m3u file and EPG.xml. Then you can test them locally in your Seebo. As if 02/03/2015, QVC Extra link is down. Need to remove it. | Rmoved Outdoor Channel (done in 1.3.5RC2). Remove USA Basketball but use this stream for Pac12. NOTE THAT: For this case, the epg.xml and playlist.m3u are loaded locally. (Have to change the settings in Settings-> Add-ons -> Enable PVR Clients -> PVR Clients -> PVR Simple IPTV Client -> Configure)
64 | Live TV |  |  | Live TV already Tuned |  | Live TV-> Context Menu button press | Press the context menu button | 5 menu options should be appeared. TV Channels, EPG:Timeline, Recordings, Timer, Search | PASS |  | TD | Search option is new in 1.3.5
65 | Live TV |  |  | Live TV already Tuned |  | Live TV-> Context Menu button press | Press each button. | TV Channels: It should go to Live TV EPG: Timeline: Should display the EPG information Recordings: Should display all recordings Timer: Should display timer view and should be able to add timers. Search: Sholud be search EPG infor and should display results | PASS |  | TD
66 | Live TV |  |  | Live TV already Tuned |  | Live TV-> Browse Channels |  | Channel Info, Icons should be populated | PASS |  | TD | Width of “GOTICA TV” logo is not enough. | USE formated logos
67 | Live TV |  |  |  |  | Live TV-> Play Channels |  | No Errors | PASS |  | TD
68 | Live TV |  |  |  |  | Live TV-> Down-> View EPG |  | No Errors | UNTESTED |  |  | Since 1.3.5 is not officially released, we didnt upload EPG.xl to FTP server. But we tested in locally after changing EPG.xml with new data. We will be sending the updated (for 1.3.5) playlist.m3u file and EPG.xml. Then you can test them locally in your Seebo. | DOWN-EPG is gone since 1.3.4. Please update this test case
69 | Live TV |  |  |  |  | Live TV-> Record Channels | Record 2-3 channels on same mux | No Errors | PASS |  | TD | There is no “start recording” message. But we saw the same message available in the previous release. But “stop recording” message is displaying when we stop the recording. | PVR XBMC messages are moved since they are not relevant to customer. Our “REC” indicates that a show is being recorded.
70 | Live TV |  |  |  |  | Live TV-> Down-> Play Recordings |  | No Errors | PASS |  | TD | Took long time and it was playing. But slow, May be the connection is slow from AUS server (139.130.88.2) to here.
71 | Live TV |  |  |  |  | Live TV-> Down-> Timer | Add a timer in 10 mins | No Errors | PASS |  | TD
72 | Live TV |  |  |  |  | Live TV-> Context Menu -> Timer | Add 3 timers start at the same time in 3 different mux | 2 out of 3 timers start without any error from VDR. | PASS |  | TD
73 | Live TV |  |  |  |  | Live TV-> Down-> Search | Search for a channel | No Errors | PASS |  |  | Tested multiple times and returned results.
74 | Live TV |  |  |  |  | Live TV-> Switch Channels | Switching between channels (15-20 channels, different mux, including a few IPTV channels) | No error. VDR is not crashing. | PASS |  | TD
75 | Live TV |  |  | Series Recording |  | Live TV ->Link Program -> Record All | Schedule at least 30 shows | Scheduled records should present in LiveTV -> Timers. Record start at expected time without error. | PASS |  | TD | Cant do series record for IPTV channels. Since they now have EPG, the LINKPROGRAM button returns a list of similar channels., and the backend of IPTVSimpleClient doesnt support this action. THIS IS FIXED IN 1.3.5RC3 | Propose to LOCK “LINKPROGRAM” button for IPTV channels
76 | Live TV |  |  |  |  | Live TV ->Link Program -> Record All. Then Stop All |  | All the timers should be deleted without any error | PASS |  | TD
77 | Live TV |  |  | VDR resilience |  | Live TV -> Record & watch LiveTV | Play/Record in two mux and then play/record in a third mux | VDR is not shutdown. There should be either a message saying “Seebo cannot play due to recording” (watch LiveTV) OR a timer is simply added (for recording) | PASS |  | TD | There is a limitation in our hardware (only 2 tuners) and this issue exists in 1.3.4.1 and previous releases.
78 | Live TV |  |  | Internet Connection |  | Live TV-> Down-> View EPG | Check IPTV and Live TV EPG | There is no EPG data available for RT. | UNTESTED |  |  | No RT data in EPG | Test case updated needed
79 | Live TV |  |  |  |  | Restart the Seebo | No of channels should be same as before restart |  | PASS |  | TD
80 | Live TV |  |  | Internet Connection |  | Switch off and switch on Seebo | Switch off and on the device several time and see do we miss any channels or EPG data get corrupted. Seebo Australia sometimes has DNS problems, hence may fail to play video. But this fails the condition of functional Internet. Symptom: “Error 110: failed to open url” message appears. A quick workaround (only when this problem occurs is to use Google DNS: Settings->Networks->Connections-><Select the Internet IP>-> Edit-> DNS-> <Change to 8.8.8.8> -> Save | Number of channels should be same and epg should be good | PASS |  | TD | We tested this here and noticed once IPTV(default) channels didnt load with reboot. Only LiveTV channels got loaded. Then we reset the PVR DB and got the IPTV channels back. Since this behaviour was strange and noticed only once, we couldnt take any decision on this.
81 | Live TV |  |  |  |  | Pause Live TV | Press pause Live TV | Live TV should be paused | PASS |  | TD
82 | Live TV |  |  |  |  | Resume Live TV | Press resume Live TV | Live TV should be resumed and EPG data should be shift accordingly | PASS |  | TD
83 | Live TV |  |  | Tune LiveTV again and reset PVR and EPG. Internet Connection |  | Check channel count for IPTV and LiveTV | Tune LiveTV again and check the behavior | We shouldn't miss any channels in IPTV and should see LiveTV channels
84 | Live TV |  |  |  |  | There will be 3 buttons. (EPG, RECORD, LINK) Each has separate functionality | EPG: show you the EPG time line. RECORD: Will allow the user to RECORD the focused channel. Button should be orange once the channel is being recorded. LINK: Will allow the user to link programs. | Respective action of each button should perform without any issues. | PASS |  | TD
85 | Live TV |  |  |  |  | Old pop-up window and left/right arrow button functionality is removed |  | Old pop-up window should not be displayed. | PASS |  | TD
86 | Live TV |  |  |  |  | Switch between channels frequently. | Keep on switching between channels | There should not be any error or/and not stopping the current playing channel. | PASS |  | TD
87 | Live TV |  |  |  |  | Delete Recordings | Go to Live TV, Start recording files, press context menu, go to Recording screen, press context menu, note there is an additional button for this screen only, i.e. Delete. When you press it recording should be deleted. | This will delete the selected recording file | PASS |  | TD
88 | Live TV |  |  |  |  | Go to Live TV>Context Menu>Search - search a text included in EPG and you will get results. | Reinstated Search functionality which we removed from 1.3.4. | All search results will appear in search window. You should be able to go up and down in the search results page. | PASS |  | TD | We added this test case, because search was not available in previous release.
89 | Live TV |  |  |  |  | When playing fullscreen and press context menu | LiveTV channel list implemented | List of Live TV channels should appear on to the right side of the screen. It should be gone when you press the menu button again. | PASS |  | TD
| Live TV |  |  |  |  | Change the focus to record, EPG, Link buttons. |  | Background should DIM by 50% | PASS |  | TD
91 | Weather |  |  | New Seebo Bootup |  | Check Weather | Weather option is removed | Weather option should not be displayed in the Global Menu List | PASS |  | TD
92 | Apps |  |  | New Seebo Bootup |  | Go to 'Apps' | Chromium browser, Facebook, Global Search, Axel Downloader, w_scan and OpenELEC Configurations should be available as applications | Chromium browser, Facebook, Global Search, Axel Downloader, w_scan and OpenELEC Configurations should be available as applications and must work without any errors. | PASS |  | TD | New Seebo logo appears in OpenELEC Configurations.
93 | Apps |  |  | New Seebo Bootup |  | Apps-> Chromium Browser | Wait approx 30 seconds | Browser should load without any Errors and should not take more than 30 secs | PASS |  | TD | Chromium browser loaded with in 8-10 secs at first time. Then it loaded within 2-3 secs.
89 | Auto Update |  |  |  |  | Check the auto-update new schedule (three times a day) | Auto-update should run three times a day Check the “cat /etc/seebo/autoupdate.cron” file And check the cron using crontab -l | It should show as follows, 0 10,18,22 * * * /etc/seebo/autoupdate.sh | PASS |  | TD
90 | Auto Update |  |  |  |  | Let the auto-update run Or run autoupdate.sh | Auto-update process should run without any errors | * backup tar should be extracted to /stroage/target/.xbmc before restart (In case backup tar will be updating) * On reboot you should see message saying "Updating KERNEL/SYSTEM/Seebo..." (backup.tar). * Once update is applied there shouldn't be /storage/target/.xmbc, /storage/.seeeboBackup and /storage/.xbmc/SeeboPatch files or folder. And /storage/.xbmc contain should be correct | UNTESTED |  |  | Need to upload the final build to update server
96 | Master Update |  |  |  |  | Settings->Network-> System->Master Update | Click “Seebo Update”. | Should popup confirmation dialog box with Yes/No option. (User will get a confirmation message.) “Please do not switch off while update is running!” If Seebo update is already running, it will popup message “Seebo update is already running” with a OK button. After this, backup tar should be extracted to /stroage/target/.xbmc before restart (In case backup tar available) | PASS |  | TD
| Master Update |  |  | After reboot |  | Apply changes while reboot |  | On reboot you should see message saying "Updating KERNEL/SYSTEM/Seebo..." as separate messages. Once update is applied there shouldn't be /storage/target/.xmbc, /storage/.seeeboBackup and /storage/.xbmc/SeeboPatch files or folder. And /storage/.xbmc contain should be correct. | PASS |  | TD
98 | Master Update |  |  |  |  | Settings->Network-> System->Master Update | Click “Master Update”, while autoupdate is running | When autoupdate is already running, it will popup message “autoupdate is already running” with a OK button. | PASS |  | TD
99 | Master Update |  |  |  |  | Stop Seebo while “Seebo update” is running and try to run the “Seebo Update” again | Checking, Forced power off situation or sudden power down situation or connection lost situation | Seebo should come back to natural state and Seebo update should start and run without any errors. | UNTESTED |  |  | Need to upload the final build to update server
100 | Master Update |  |  |  |  | Check the functionality of Seebo after Master update/Auto update | After completed Master/Auto update, Seebo should test for all functionality | After completed Master/Auto update, Seebo should properly ported last version and nothing has to be broken. | UNTESTED |  |  | Need to upload the final build to update server

## Document History
Document Version | Test Case | Status | By | Date
1.0.0 | All | Added | DA | 2014-11-11

## Data (hidden)
-
DA | PASS | Added
TW | FAIL | Deleted
KJ | UNTESTED | Modified
DM
JS
TD