## Product Overview
Seebo CURRENT Software Baseline Release: | Version 1.3.5.1 (Released)
Seebo Software Original Release : | 1.3.0 Released 30/10/2014
Seebo (AKA MINI) Prototype Release Date: | Feburary 2015 (Released)
Seebo (AKA MINI) Commerical Alpha (Sales Demo) | End March 2015 (Confirmed)
Seebo COMBI | End March 2015 (Prototype)
Seebo SIX Protoype Release Date: | Late Feburary 2015 (In Testing)
Seebo ECO Server Release Date: | March 2015 (Prototype)
Document Revision: | 4.17
Revision Date: | 2015-03-18
EDT= Estimated Delivery Time (Within 48 hours)
Project Status Colour Codes
GREEN TEXT=Is Live/Active Projects
REDTEXT = Completed Project/Closed
BLACK TEXT = On Hold or TBA
BLUETEXT = Feature Delivered, awaiting testing.

## Release Schedule
Seebo MAXX Software Release Schedule:
Release of functionality:All feature releases are via the auto updated processed, with all devices connected to the internet Polling Seebo SVN server. All Beta releases have been tested by an internal Seebo staff member and by David Mitchell, signing off before release. This is a documented process, testing that new functionality has not affected any other feature or service performance.
Target Date | Features/Updates/Bug Fixes/UX Enhancement | Release Version | Comments
2014-10-01 | BASE LINE Seebo Refer to user manual for features | 1.3.0 | Base Line Commercial Beta release
RELEASED
November 27/11/2014 | BASE LINE with pre-release tested functionality | 1.3.1 | Revised Commercial release
RELEASED
BUG FIX: Corrects Pixilation issue with LIVE TV scanning and playback. Correction of Channel 31 interfence.
Dec 09/12/2014 RELEASED | UX Enhancement: On Demand Add-On Channels LINKS and IONS pre-populated providing the User a faster add-on install process, rather than waiting for links to update manually. Check Content Update for List. | 1.3.2 | Commercial Beta Release -
| UX Enhancement: Removed Weather Channel. |  | 1.3.2 Release will become the NEW BASE LINE Release for all default NEW installed Seebo devices.
UX Enhancement: Removal of the "Registration" page on USERS first device set-up process.
Jan 19/01/2015 RELEASED | NEW FEATURE: Official Release of uCAST 1.0.1. SeeDocs and Axis only channels. K4Kids, M1, M2 and S4Sport feature "Coming Soon". | 1.3.3 | Release of uCAST SeeDocs and Axis (Axis will have a parental control)
UX Enhancement: Remove BACK Button instances in Sub Menu Setting/System Info
UX Enhancement: Remove BACK Button instances in Sub Menu Settings/Networks.
BUG FIX: Update Australian National Terrestrial Multiplex's frequency ranges.
BUG FIX: VEVO and Youtube Fix. Channel 1 review. Please note these are not Seebo's channels we are correctting.
UX Enhancement: Content Update On Demand/Music.
UX Enhancement: Simplified user Dialouge located on bottom right hand screen advising user of update progress and that the update is complete. User Dialouge remains on screen until the user has restarted their Seebo. This way we force the update.
Jan 19/01/2015 RELEASED | UX Enhancement: Addition of a 'HELP' feature to the main menu. This is a text BASED version with a scheduled interactive upgrade. | 1.3.4rc2 | Commercial Beta Release.
| UX Enhancement: Re Format Setting/Add-Ons to conform to the same GUI global format. Remove all ICONS have as list. |  | Version 1.3.3 and 1.3.4 have been combined as Single release.
| UX Enhancement: Remove access to the functionality when the user clicks back on Sub Menu. These need to appear as a pop-up when the user clicks the "Menu" button on the remote. This applies to On Demand, Music and Apps. |  | 1.3.4rc2 is NOW OFFICIAL BASELINE Commerical BETA release
UX Enhancement: Enhanced New Version Release USER Update Dialouge.
UX Enhancement: Add a button to the LEFT menu at base of menu list Setting/System/ after "Master Lock". The Button is to be called 'System Update'.
UX Enhancement: Feature to Pause Live TV.
UX Enhancement: Work Flow Modification. This feature has already been developed. This is the feature that allows users to click down to access the RECORD, LINK, SHARE AND UPDATE EPG FEATURE.
Feb 16/02/2015 RELEASED | BUG FIX: UpdateChannel Switching BUG (speed issue) | 1.3.4.1 | Refer to "RoadMap (Tasks)" Sheet for release funtions, features, user enhacements and Bug Fixes.
CONTENT UPDATE: Release New Youtube Add On
March 06/03/2015 RELEASED | Offical Feature/update release specification 20/02/2015 | 1.3.5 | Official Software Commerical Beta BASELINE version. Refer to "RoadMap (Tasks)" Sheet for release funtions, features, user enhacements and Bug Fixes.
March 16/03/2015 | PATCH: Add button to manually control system updated and refesh. Feature to appear in SETTINGS -> SYSTEM->SEEBO UPDATES-> Refresh and Update. | 1.3.5.1 | Target release date confirmed.
March 31/03/2015 | Official Seebo Software and Hardware Device Software Release. | 1.0.1 | Seebo Standard Software.

## RoadMap (Tasks)
RID | Description | Priority | Status | Version | Owner | Assignee | EDT | Comments
Seebo Software
1 | Build OE 5.0 with Kodi (14.0) SEEBO MAXX and SEEBO MINI merged builds. | High | On hold | 2.0.0 | Dhan | TDG/Dhan/Skinny Jin | Review 23/02/2015 | Merge will take place with version 2.0.0.
2 | Add Prime and WIN default Logos for LIVE TV channels. | Medium | On hold |  | TGD | Dave | Review March | Dave and Tuan to meet and discuss ideas.
3 | Clean Up of all ICONS | Low | In Progress | 1.3.6 | Dhan | Dave | ETD 24/03/2015 | Dave to provide all instances if ICON modifications and document to Dhan.
4 | Formalise Software Update/Bug Fix Release procedure to SVN. | High | Closed | 1.3.5 | Dave | Dhan | Delievered | Dave and Dhan to meet and discuss ideas. 12.00pm SL time.
5 | Upgrade Whether Channel to be customisable. This includes Three default interfaces. Sailing, Fishing and Surfing. This consists of modifying the current Synoptic Chart ID's. These Modifications will only relate to Australia and New Zealand. Other countries will require additional data sources. | Low | On hold | TBA | Dave |  | On Hold | Expected only EDT. DM to provide full spec. Requires further clarifications
6 | Seebo Mobile Application: This is an extension of XBMC's current mobile application. The source is readily available. This application does not work successfully. It does not access the users mobile data, only displays Content being played on the XBMC device. | High | Closed |  | Dhan | N/a | N/a | This requires further clarification. If you require source. Please advise. Requires further clarifications. Does this involve Android / IOS app development ? Would require additional equipment ? Forms Part of projects 17 and 20. Now Closed.
7 | SeeLiveTV (Simple IPTV Client). This feature has already been developed. However it is unstable with the current baseline build. | High | Closed | 1.3.3 | STM | TGD | Delivered | Final round of testing ready. Migrating uCAST to 1.3.2 for final rtesting. Roll back issue was based on poor VDR build… concurrently not running on test machine. List of Content in Content Update
8 | Work Flow Modification. This feature has already been developed. This is the feature that allows users to click down to access the RECORD, LINK, SHARE AND UPDATE EPG FEATURE. | High | Closed | 1.3.4 | T Bird | Dave | Delivered | Dave to send ICONS to T'Bird for LIVE TV. Dave to respond to SL with Sub Menu Modifications. LIVE TV
9 | Multi-Screen. XBMC currently supports Multi Screen Playback. This feature allows the user to switch what they are "watching" to their Seebo Device. This is/was a feature. However the modifications made to Seebo has made it very unstable. While fixing this feature we need to able the capability to allow the user Switch what they are watching on Seebo to another device mobile or Seebo Mini. | Medium | On hold |  | Dave |  |  | DM to explain in detail.
11 | ADD "Help" to Seebo main navigation. Video Help currently being investigated - TBM to respond at next review. | High | Closed | 1.3.5 | Big Man | TBird / Dave | Delivered | Dave to Submit the final round of GUI MODS and workflow to The Big Man 16 Feb 2015
11.1 | Integrating a Online chat with Seebo Support team and population of Set-Up Videos | Medium | On hold |  | Big Man | Dhan | On Hold | Add a online chat feature to the Help screen that connects to Seebo's Online helpdesk chat centre. This will include Set-Up and trouble shooting videos.
13.A | Seebo MINI PCBA and Gerber modifications (Completed): 1. WiFi antenna to be 7Dbi 2. Add Seebo LOGO S 3. Add Dual Tuner DVB-T 4. Modify USB to cater for USB pin header for DVB-T 5. Modify IR header to RF header and change to 7 pin with dual GND. 6. Add LED Loom 7. Resolve heat vent issue to a limit condition of 60dc | High | Closed | 1.0.1 MINI | Dave | Skinny Jin. | Delivered | 1. PCM driver for audio out - Currently, Seebo Mini has only audio output driver as an analog. - It can be output sound to HDMI. The audio jack attached the device is not working. - The sound hardware which is built in by default has two devices, one of them is for HDMI and S/PDIF another is external audio out. I have plan to output these device at the same time by ALSA (Advabced Linux Sound Architecture). 2. Remote controller - Seebo Mini use a remote controller as same with Seebo Maxx. - An automatic scrolling when a button is pressed is not working. - For example, to pump up volume, the button for v. up should be pressed one by one. - I am considering to modify xbmc source cord in xbmc/application.cpp 3. Not working the channel of US Twit in [Live TV] - The channel has [FLV] format as a codec. - The channel is working in [On Demand] - Recently, I have changed uCast list only for Seebo Mini, playlist-mini.m3u removed that channel. 4. Online update for Seebo Mini - There is no way to update Mini's firmware via "http://updates.seebo.com.au" yet. - I need to test more the cron service for regular update. This now forms part of Seebo (AKA MINI) Project. Refer Below
13.B | SeebO MINI Update Server. | High | Closed | 1.0.1 | Skinny Jin | Tuan/Dave/Dhan | Closed | This now forms part of Seebo (AKA MINI) Project. Refer Below
13.1 | Start reviewing how to embbed Seebo Software on NAND flash. | Low | On hold |  | Skinny Jin | Dave | Closed | This now forms part of Seebo (AKA MINI) Project. Refer Below
14 | Commence formal BOM Costing for Seebo MINI as prototype is 95% complete. | High | Closed | 1.0.1 | Dave | David | Delivered | This now forms part of Seebo (AKA MINI) Project. Refer Below
15 | Seebo Version 2.0 | High | On hold | 2.0.0 | Dave | Dhan | Review 13/03/2015 | A new GUI workflow design post as outlined by Entertaining Environments. Refer to One Page Document Titled: Seebo Version 2.0 Overview.
16 | Seebo ECO (Seebo SIX) (Seebo in Rack mount Server form factor with standard 3 zones) | High | Closed | 1.0.1 MINI | Dave | Skinny Jin/Tuan | Closed | I/O Interfaces to include 3 zones, HDMI, 3RCA, Terrestrial over CAT6e, DVB-T, DVB-C and DVB-S, PAL Female and F Connector. This now forms part of Seebo (AKA MINI) Project. Refer Below
17 | Seebo MOBILE APPLICATION. iOS / Andrioid App for Seebo. | High | In Progress | 1.3.6 | TBM | Rose/Indy/Skinny Jin | Review 23/02/2015 | Dave to design up GUI and Feature requirements and send to SNL by 11/02/2015. Skinny Jin to assist with iOS and Andriod VDR… advice only. REFER to Project 20… as they will merge as part of the same build. First designs to SNL 20/02/2015
18 | NEW YouTube channel. | High | Closed | 1.3.4.1 | Bash | TBird/ STM | Delievered | Refer to Content Updates. 1.3.4.1
18.1 | SeeLIVE TV Channel Build Template - Was uCast | High | Closed | 1.3.5 | Bhash | Tbird doing Axis. | Delivered | Bhash to upload the LIVE/On Demand SeeLiveTV directory template. Offcial Release AXIS is 1.3.5
19 | Feature to Pause Live TV | High | Closed | 1.3.4 | STM | Tuan/STM | Delivered | Technically referred to as "Time shifting". Gotham still has unmatched EPG issues. Check Kodi. If working, migrate configurations of vdr/vnsi plugins to 12.2.
20 | Streaming Live TV and other stored recording TV Vidoes over (WAN/LAN) on UPnP and Airplay… Reinstate AIRPLAY and UPnP file sharing on all devices. | High | In Progress | 1.3.6 | Dhan | Sammy | Delivered | Dave/Jin to delve a deeper into this. Project REF with 17. Mobile.
21 | Remove BACK Button instances in Sub Menu Settings/Networks | High | Closed | 1.3.3 | Dhan | T'Bird/TBM | Delivered
22 | Remove BACK Button instances in Sub Menu Setting/System Info | High | Closed | 1.3.3 | Dhan | T'Bird/TBM | Delivered
23 | Re Format Setting/Add-Ons to conform to the same GUI global format. Remove all ICONS have as list. | High | Closed | 1.3.4 | Dhan | T'Bird/TBM/Dave | Delivered | Refer to Point 8. GUI Updates. Forms part of this project. Dave to send list of Add-ON menu feature requirements.
24 | Update Australian National Terrestrial Multiplex's frequency ranges. (Refer Attached Documents). | High | Closed | 1.3.3 | Dhan | Tuan | Delivered | Refer to Documents Attached on email circulated Mon 8/12/2014 5:17 PM. This is an URGENT Requirement. Solution is Auto Australia. Make as Default. Shall include this in 1.3.3
25 | Texture embedded/rendering is a legacy of Dave Horne's crappy code. This is effecting the channel uploading. | High | In Progress | 1.3.6 | Dave | Dave | Review 13/03/2015 | Refer to Point 8. GUI Updates. Forms Part of this project
26 | Remove access to the functionality when the user clicks back on Sub Menu. These need to appear as a pop-up when the user clicks the "Menu" button on the remote. This applies to On Demand, Music and Apps. | High | Closed | 1.3.4 | Dhan | TBM | Delivered | Refer to Point 8. GUI Updates. Forms Part of this project. Dave to Send Screen shot. Still to be confirmed.
27 | Replace the Seebo/XBMC version of Seebo Software Release on Setting/System Info/Summary with ONLY the Seebo Updated Version of Seebo. | High | Closed | 1.3.3 | STM |  | Delivered
28 | Add a button to the LEFT menu at base of menu list Setting/System/ after "Master Lock". The Button is to be called 'System Update'. | High | Closed | 1.3.4 | Dave | TBM | Delivered | On the Right Screen, the User can select an UPDATE Button. This Button Calls our SVN server and checks for an update. If an update is required, the USER can see a progress BAR…
29 | Enhanced New Version Release USER Update Dialouge. | High | Closed | 1.3.5 | Dave | T'Bird/TBM | Delivered | Refer to list
31 | SeeLiveTV Music Video Channel. Adminstered by Seebo. | Medium | Closed | 1.3.6 | Dave | Dave/Bhash | Delivered | Channel Template Complete. Bash to send Documentation to upload content. Refer to SeeLiveTV
32 | Factory Reset | High | On hold | 2.0.0 | Dhan | Dave/TBM
33 | Implement Unicode/UFT-8 Arial | Medium | In Progress | 1.3.6 | Dhan | Dave/STM | Review April 2015 | Implement Arial UnicodeUFT-8.
34 | Content Recommendations GUI | High | On hold | 1.3.6 | Dhan | Stan/T'Bird
35 | Reinstate Delete Past LIVE TV Recordings. | High | Closed | 1.3.5 | T'Bird | T'Bird/Tuan | Delivered | TGD to send the video of post testing T'Bird and CC to STM. Improve currrent code stability. Buggy.
36 | Feature to Select ALL Series Recording | High | Closed | 1.3.5 | TGD | T'Bird/TGD | Delivered | After feature implemented. User Dialouge. Bug for T'Bird. New BUG for VDR Client. Bug Resides at the VDR core. Tuan hunt for Root Cause. Series recording not implemented. Multi recording has been implemented
37 | Press OK to Show LIVE TV LIST. Displays list of Channel when MENU button is selected to marry current work flow. | High | Closed | 1.3.5 | TGD | TBM/Dhan | Delivered | T'Bird and TGD to review
38 | Parental Control (Default LOCKED For Axis) | High | In Progress | 1.3.6 | T'Bird | T'Bird/Stan | ETD 31/03/2015 | David to Review workflow process and approve. Partially working. Takes 10 mins to apply PC
39 | Small Description on SeeLiveTV | High | Closed | 1.3.5 | Dave | T'Bird/Stan/Dave | Delivered | TGD to provide Dave epg.xml. On SVN server. Jin to show Tuan where epg.xml resides on server.
40 | Seebo Update Protocol. Update the "update" Script. | High | Closed | 1.3.5 | Tuan | Dhan/Stan | Delivered | Rethink and review on review date.
41 | When LIVE EPG/Record/Series Link is selcted, EGP text and LOGO DIMS by 50%. | High | Closed | 1.3.5 | Dave | Tuan/T'Bird | Delivered | Dave and T'Bird.
42 | Must be able to select Main Menu even when in OnFocus EPG/Record/Series Link | High | Closed | 1.3.5 | T'Bird | T'Bird | Delivered
43 | CDN and for LIVE Streaming. | High | In Progress | 1.3.6 | Dave | Dave | Review 23/03/2015 | Dave to locate a cheap price per data.
44 | RELEASE Content Review and Update Process | High | Closed | 1.3.5 | Bhash | Bhash | Delivered | Standard Process.
45 | Channel EPG OnFocus to call the entire EPG. | High | Closed | 1.3.5 | Dhan | TGD | Delivered
46 | Screen go black switching between channels | High | On hold | 1.3.6 | Nick | Rob | Waiting Busines case from Sales as this is USER Preference | Remove buffering message. Dave to get back to us after discussion
47 | On Focus Live TV channels disappear when selected. | High | On hold | 1.3.6 | Nick | Rob | Waiting Busines case from Sales as this is USER Preference
48 | Reinstate EPG SEARCH feature. | High | Closed | 1.3.5 | TGD | Tbird | Delivered | OnFocus issue. Bug Fix required.
49 | MD5 on UPDATE Server providing the user False Positives | High | Closed | 1.3.5 | Kass | TGD | Delivered | Change the Auto Update on Monday/Month End Running the update/ 10am/6pm/10pm AEST
50 | Channel Switching BUG (speed issue) | High | Closed | 1.3.4.1 | STM | TGD | Delivered
51 | EPG conflict with Simple IPTV Client and Timing Sever | High | Closed | 1.3.5 | STM | TGD | Delivered
52 | In ability to read "unknown" codec format. | High | Closed | 1.3.5 | TGD | TGD | Delivered | Update codec / libraries for Seebo – Maxx and Mini
53 | Manual Update Bug Fix – Incorrect progress message | Medium | Closed | 1.3.5 | Kass |  | Delivered
54 | SeeTube – Youtube channel for Seebo | Meduim | On hold | 1.3.6 | Bhash | Kass | Review 23/03/2015
55 | Dependency issues for addons | High | Closed | 1.3.5 | TGD |  | Delivered | Python libraries updated
59 | Change “Buffering” instances to “Loading” for LiveTV, OnDemand, Music. | High | Testing | 1.3.6 | T Bird |  | Testing | Users are used to “Loading” as a sense of waiting and tend to have patience. “Buffering” seems to suggests slow, error.
60 | Update END USER CASE TEST SCENARIO (replicate customer condition) | High | In Progress | 1.3.6 | Kass | Dave | Review 23/03/2015 | Dave and Kass to Map out a END User TEST Senario… (Not DEV)
61 | Remove all the cross (X) in the information banners | High | Testing | 1.3.6 | T Bird |  | Testing
62 | Include Dialogues for “Record” & “LinkProgram” for SeeTV channels | High | Testing | 1.3.6 | T Bird |  | Testing | Give user dialogues inform SeeTV can't be recorded or linked (Features not supported)
63 | Develop new “Delete ALL” features for Recordings | High | Testing | 1.3.6 | TGD |  | Review 20/03/2015
64 | Improve functionality user dialogues for Wifi | High | In Progress | 1.3.6 | Sam |  | Review 20/03/2015
65 | Improve user dialogue/user expectation for COLD update | High | Testing | 1.3.6 | Kass |  | Testing | Add “Please wait” when proper. Send all the unncessary logs to the background or a debug log file
66 | Add a “Delete” button to delete an entry in LiveTV -> Timer | Meduim | On hold | 1.4.0 | Tuan |  | Review 31/03/2015
67 | Add sliding capability for show's title in LiveTV | Medium | Testing | 1.3.6 | Sam |  | Testing | Some titles are too long to read (if not moving). For example, RT, SBS One (sometimes), Extra (sometimes), 1HD
68 | Fix the ICON pop-up for autoupdate. Use Seebo ICON | Medium | In Progress | 1.3.6 | STM |  | Review 23/03/2015 | At the moment, it shows random ICONs.Fix for 1.3.6. and it takes effective in later releases
69 | Add “Update SeeLive TV ” under Setting -> LiveTV | High | Closed |  |  |  | Closed. | To allow user to choose a customised SeeLive TV list (Chinese, Greek, Japanese, etc.) and then Seebo will do needed configurations. Lists can be prepared in ftp server. Project MERGE with 17. Mobile. Project MERGE with Task 74.
70 | Give proper ICON for recorded show in LiveTV->Recordings | High | On hold | 1.4.0 |  |  |  | Go to Recordings, the show has EPG info but no ICON
71 | Remove the word “Compiled” in Settings -> System Info (first line) | Medium | Testing | 1.3.6 | Kass |  | Testing
72 | Fix the CPU & GPU temperatures in Settings -> Hardware | High | On hold | 2.0.0 |  |  |  | Gotham build on our seebo max has info for CPU and GPU temperatures
73 | Create a test build to get the detailed logs for failed updates | High | Testing | 1.3.6 | TGD |  | Review 20/03/2015 | To assist us and our partner to investigate failed download issue
74 | Acquire a List of Geo and Languge Based Channels | High | Testing | 1.3.6 | Bhash | Dave | Review 20/03/2015 | International Geo Based Lanagaue Channel to be built into SeeLiveTV format include. Greek, Arabic and Chinese.
75 | Build an API inhertanly integrated into the Set-Up wizard that enbales end user selection of languge based channels. | High | In Progress | 1.3.6 | T'Bird | Dave | Review 20/03/2015 | Dave to provide details
76 | System Refresh. Button. To forces system reset and impose 1.3.5 version update if update Error occurs. | High | Testing | 1.3.5.1 | Kass | Dhan | Testing | Set for 1.3.5.1 shipping 23/03/2015.
77 | Set EPG Record Times to 140minutes as default or Record to the EPG time line for the Recording parameters in the LIVE TV settings. | High | In Progress | 1.3.6 | T'Bird | TGD / Dave | Review 20/03/2015 | Tuan to confirm dependency between EPG and recording
78 | Skin Spotify | High | In Progress | 1.3.6 | T'Bird | Dhan | Review 20/03/2015 | These are apps that have been tested and working. Dave to provide base Design (GUI)
78.1 | Skin Pandora | High | In Progress | 1.3.6 | Bhash | Dhan | Review 20/03/2015 | These are apps that have been tested and working. Dave to provide base Design (GUI)
78.2 | Build Ultravilot APP. | High | In Progress | 1.3.6 | Sam | Dhan | Review 20/03/2015 | These are apps that have been tested and working. Dave to provide base Design (GUI)
79 | Rego Page and Lanaguges. | High | In Progress | 1.3.6 | Dave | T'Bird | Review 20/03/2015 | Dave to provide the REGO page and workflow process including data parsing diagram.
Seebo Mobile Application |  | Seebo Mobile
1 | Setup Project for Andrioid | High | Closed | 0.0.1 | Indi |  | Delivered
2 | Setup Project for IOS | High | In Progress | 0.0.1 | Indi | STM, Dave | Review 27/03/2015 | Requires a MAC to complete
3 | RnD on VDR Client for Andriod | High | Closed | 0.0.1 | Indi | STM, Dave | Delivered
4 | RnD on VDR Client for IOS | High | In Progress | 0.0.1 | Indi | STM, Dave | Review 18/03/2015 | Requires a MAC to complete
5 | Seebo Mobile – Andriod Alpha | High | In Progress | 0.0.1 | Indi | STM, Dave | Review 23/03/2015 | Nearly complete awating final ICON images from Dave
6 | Seebo Mobile – IOS Alpha | High | In Progress | 0.0.1 | Indi | STM, Dave | Review 27/03/2015 | Requires a MAC to complete
7 | First CUT GUI layout with typography | High | In Progress | 0.0.1 | Indi | STM, Dave | Review 23/03/2015 | Nearly complete awating final ICON images from Dave
8 | Supply ICONS as all separate images. | High | In Progress | 0.0.1 | Dave |  | ETD 17/03/2015
9 | Set-UP Fast Upload at daveds House to Increase LiveTv Speed. | High | In Progress | 0.0.1 | Dave |  | ETD 23/03/2015
Seebo (AKA MINI) AMLogic s802
1 | Test build for Seebo Maxx with OE4.2+Gotham | High | In Progress | 1.0.1 | Skinny Jin | Kass, T'Bird, STM | Review 20/03/2015 | SNL to conduct final EVAL and respond.
2 | Output audio signal to S/PDIF | High | Testing | 1.0.1 | Skinny Jin |  | Review 20/03/2015 | Need to be selected the device by boot time, currently, the device(S/PDIF) is selected By manual modification with asound.conf file.
3 | Update the firmware with zip file | Medium | Testing | 1.0.1 | Skinny Jin | Kass, T'Bird, STM | Review 20/03/2015 | Need some software method to boot on “recovery mode- Android mode” like bios boot Need to add a package for Android.
4 | Redesign the update mechanism for Mini Release | Medium | In Progress | 1.0.1 | Skinny Jin | Kass, T'Bird, STM | Review 20/03/2015 | Same method as Seebo ECO/SIX/MINI…
5 | Draft ROM NAND Flash install procedure for Xlintek | High | In Progress | 1.0.1 | Skinny Jin | Kass, T'Bird, STM | Review 20/03/2015 | An extension of what was written for SNL
6 | Seebo Update Server. | High | In Progress | 1.0.1 | Skinny Jin | Tuan/Dave/Dhan | Review 20/03/2015
Seebo SIX
1 | Baseline Hardware for the DVB-T 6 tuner | High | Testing | 1.0.1 | Dave | Tuan | Review 20/03/2015 | 6 tuner PCBA appears to be working. Testing result appear to be sucsessful.
2 | MINI PCIe socket causes WiFi interface defect. | High | In Progress | 1.0.1 | Dave |  | Review 20/03/2015 | Need to create system LOG to isolate if reconfiguring MSATA port to USB Host is the cause. Could have drive related issues. Have to send Log result to Giadia.
3 | GUI design for ECO system "AUTO DEVICE DISCOVERY" | High | In Progress | 1.0.1 | Dave | Kass, T'Bird. | Review 20/03/2015 | Design GUI screen shots for workflow guide.
4 | Investigate into adding an additional HMDI INPUT to plug in additional hardware device. | High | In Progress | 1.0.1 | Dave |  | Review 20/03/2015 | Look into designing a external HDMI on PCB. Possible use 24 PIN header to add physical interface.
Seebo COMBI
1 | Mike Lenehan finalising Speaker Enclosure | High | In Progress | 1.0.0 | Dave | Mike Lenehan | ETD 19/03/2015 | Final round of prototypes shipped with 5 Inch driver and 50% more woofer excusion, increase enclosure size over Proto2 by 21%. This will yeild the bas response required.
2 | Amplifier's 200w at 4 Ohm load coupled with Power supply | High | Testing | 1.0.0 | Skinny Jin | Dave | Review 13/03/2015 | Experiacing power supply issues with sample D Class Amp
3 | Start to assemble BOM costing | Medium | In Progress | 1.0.0 | Dave |  | Review 20/03/2015 | Need some software method to boot on “recovery mode- Android mode” like bios boot Need to add a package for Android.
Seebo ECO Server
1 | GUI design for ECO system "AUTO DEVICE DISCOVERY" | High | In Progress | 1.0.1 | Dave |  |  | Refer project "Seebo Six" task 3.
SeeLiveTV |  |  |  | Software
1 | Reinstate Channels: VTV, Pentegon, Gothic TV, Lobas TV | High | In Progress | 1.3.5.1 | Bhash |  | ETD 13/03/2015 | Upload config file m3u… for 1.3.5 orginal.
2 | Test: Porsche TV, BMW TV, Fashion HD TV and Arirang TV | High | Testing | 1.3.5.2 | Bhash |  |  | Testing for 14 days required prior to uplaoding.
3 | SeeLiveTV Music Video Channel. Adminstered by Seebo. Master Channel Template | Medium | Testing | 1.3.6 | Dave | Dave/Bhash | Delivered | Channel Template Complete. Bash to send Documentation to upload content.

## Content Release
NB: All content Not Lists on the Release Version (Below) should not appear on the Default Pre Loaded Content Library.
Pre Loaded Default List.
Version 1.3.2 |  |  | Version 1.3.3 |  |  | Version 1.3.4 |  |  |  | Version 1.3.5 |  |  |  | Version 1.3.5.1
On Deamand | Music | Apps | On Deamand | Music | Apps | On Deamand | SeeLiveTV | Music | Apps | On Deamand | SeeLiveTV | Music | Apps | On Deamand | SeeLiveTV | Music | Apps
ABC iVIEW | Radio Tunes | Chromium | ABC iVIEW | Radio Tunes | Chromium | Sports Devil. (New) | USTwit |  |  | Sports Devil. (New) | USTwit | Radio Tunes |  | Sports Devil. (New) | USTwit | Radio Tunes
AFL Video | Tripple R | Global Search | AFL Video | Tripple R | Global Search | ABC iVIEW | Rock&Co. (Shopping) |  |  | ABC iVIEW | Rock&Co. (Shopping) | Tripple R |  | ABC iVIEW | Rock&Co. (Shopping) | Tripple R
Al-jazeera (Office) |  |  | Al-jazeera (Official) |  |  | AFL Video |  |  |  | AFL Video | AXIS Adult (Offical Release) | Sonos |  | AFL Video | AXIS Adult (Offical Release) | Sonos
Best Of YouTube |  |  | Best Of YouTube |  |  | Al-jazeera (Official) | QVC TV UK (Shopping) |  |  | Al-jazeera (Official) | QVC TV UK (Shopping) |  |  | Al-jazeera (Official) | QVC TV UK (Shopping)
Betty's Kitchen |  |  | Betty's Kitchen |  |  | Best Of YouTube |  |  |  | Best Of YouTube | SeeMusic (Offical Release) |  |  | Best Of YouTube | SeeMusic (Offical Release)
CBS News |  |  | CBS News |  |  | Betty's Kitchen | HSV TV (Shopping) |  |  | Betty's Kitchen | HSV TV (Shopping) |  |  | Betty's Kitchen | HSV TV (Shopping)
Discovery Networks | [5 empty] | CBS News |  |  |  | CBS News |  |  |  | CBS News
ESPN Video |  |  | ESPN Video |  |  | ESPN Video | RT (Documentry) |  |  | ESPN Video | RT (Documentry) |  |  | ESPN Video | RT (Documentry)
Food Network |  |  | Food Network |  |  | Food Network (Updated) |  |  |  | Food Network (Updated) |  |  |  | Food Network (Updated)
GoPro (Official) |  |  | GoPro (Official) |  |  | GoPro (Official) |  |  |  | GoPro (Official) |  |  |  | GoPro (Official)
NBA Replays |  |  | NBA Replays |  |  | NBA Replays |  |  |  | NBA Replays |  |  |  | NBA Replays
REDBULL (Official) |  |  | REDBULL (Official) |  |  | REDBULL (Official) |  |  |  | REDBULL (Official) |  |  |  | REDBULL (Official)
SeeDocs (Official) |  |  | SeeDocs (Official) |  |  | SeeDocs (Official) |  |  |  | SeeDocs (Official) |  |  |  | SeeDocs (Official)
Sports Illustrated |  |  | Sports Illustrated |  |  | Sports Illustrated |  |  |  | Sports Illustrated |  |  |  | Sports Illustrated
Ted Talks |  |  | Ted Talks |  |  | Ted Talks |  |  |  | Ted Talks |  |  |  | Ted Talks
TMZ |  |  | TMZ |  |  | TMZ |  |  |  | TMZ |  |  |  | TMZ
Victoria's Secret |  |  | Victoria's Secret |  |  | Victoria's Secret |  |  |  | Victoria's Secret |  |  |  | Victoria's Secret
World News Live |  |  | World News Live |  |  | World News Live |  |  |  | World News Live |  |  |  | World News Live
WWE Online |  |  | WWE Online |  |  | WWE Online |  |  |  | WWE Online |  |  |  | WWE Online
YouTube |  |  | YouTube (Alpha29) |  |  | YouTube |  |  |  | YouTube |  |  |  | YouTube
|  |  | VEVO (Official) |  |  | VEVO (Official) |  |  |  | VEVO (Official) |  |  |  | VEVO (Official)
|  |  | TV4ME |  |  | TV4ME |  |  |  | TV4ME |  |  |  | TV4ME
[6 empty] | 1Channel |  |  |  | 1Channel |  |  |  | 1Channel
[10 empty] | Axis (Adult Channel) |  |  |  | Axis (Adult Channel)

## Stakeholders (hidden)
High | Dhan | Closed
Medium | Dave | On hold
Low | T'Bird | In Progress
| TBM | Testing
Bhash
STM
TGD
Bad Gin
Nick
Steve
Manju